## User Stories
US-### | STORY PTS | TO DO | IN PROGRESS | WAITING FOR REVIEW | FINISHED
1 | 3 | As a complaint analyst, I want the AI Agent to be able to determine whether something is a complaint, so that irrelevant information is ignored.
2 | 5 | As a complaint analyst, I want the AI Agent to ingest complaints from phone transcripts, so that customer issues can be investigated from phone calls and voicemails.
3 | 5 | As a complain analyst, I want the AI Agent to ingest complaints from web requests, so that customer issues can be investigated from messages through our website.
4 | 5 | As a complaint analyst, I want the AI Agent to ingest complaints from emails, so that customer issues can be investigated from my inbox.
5 | 5 | As a complaint analyst, I want the AI Agent to ingest complaints from different branches, so that customer issues can be investigated more effectively.
6 | 2 | As a complaint analyst, I want the AI Agent to be able to retrieve customer information from structured data, so that relevant information can be gathered.
7 | 3 | As a complaint analyst, I want the AI Agent to be able to retrieve policy information, so that relevant policies can be applied.
8 | 1 | As a complaint analyst, I want the AI Agent to be able to flag missing information, so that I can review it.
9 | 3 | As a complaint analyst, I want the AI Agent to be able to summarize the information, so that I can review it.
10 | 5 | As a complaint analyst, I want the AI Agent to be able to use the compiled information to suggest next actions, so that I can make a judgement call.
11 | 1 | As a complaint analyst, I want the AI Agent to be able to categorize the urgency of complaints, so they can be escalated to a supervisor.
12 | 3 | As a complaint analyst, I want the AI Agent to be able to escalate summaries to a supervisor, so that they can review sensitive, uncertain, high risk, or compensatory information before the action is taken.
13 | 2 | As a complaint analyst, I want the AI Agent to record each step in the complaint analysis process in its audit logs, so that they can be reviewed by my supervisor as necessary

## Acceptance Criteria
US ### | ACCEPTANCE CRITERIA
1 | Given a field of text, AI Agent will determine whether or not a complaint is present
1 | If a complaint is present, the AI will open a complaint ticket
1 | If a complaint is not present, the AI will ignore the information
2 | Given a phone complaint, AI Agent will identify and catalog all relevant information
2 | Agent will catalog customer narrative
2 | Agent will catalog customer information
3 | Given a web complaint, AI agent will identify and catalog all relevant information
3 | Agent will catalog customer narrative
3 | Agent will catalog customer information
4 | Given a complaint email, AI agent will identify and catalog all relevant information
4 | Agent will catalog customer narrative
4 | Agent will catalog customer information
5 | Given a branch complaint, AI agent will identify and catalog all relevant information
5 | Agent will catalog customer narrative
5 | Agent will catalog customer information
6 | Given a complaint ticket, AI agent will be able to access SQL databases to search for customer information
6 | Agent will gather all relevant information on the customer in question
6 | Agent will not gather any information from other customers
7 | Given a complaint ticket, AI agent will be able to use RAGs to search for policy information
7 | Agent will gather all relevant policy information for the complaint in question
7 | Agent will not gather any irrelevant policy information
8 | AI Agent will check off each field of customer information as it goes
8 | Whatever unchecked fields remain will be flagged as missing
8 | AI Agent will record this in the audit logs
9 | AI Agent will compile policy and customer information
9 | AI Agent will write a written summary of the information on hand
10 | AI Agent will reference the written summary and policy information to provide next steps
10 | AI Agent will inform the analyst if it does not have enough information
10 | AI Agent will record this in the audit logs
11 | AI Agent will compare the customer and policy information to urgency rules to present the urgency of each case
12 | AI Agent will route the case to a supervisor if the urgency reaches a certain threshold
12 | AI Agent will record this in its audit logs
13 | AI Agent will stop at each step of the analysis
13 | AI Agent will record previous action in the logs
13 | AI Agent will record analyst, supervisor, and customer information in the logs